## STB Scripts
Task Name | Qty | Due Date | Done | Assigned To | Status | Notes | Comments
STB RS Implementation (RS + RSF)
ROOTSTOCK FINANCIALS
SET-UP (Use 'Getting Started with Rootstock Financials' Document as Guide)
Create Financial System User (requires Manufacturing User) | [5 empty] | New User can access financials system objects
Create Financial Company Master(s) and validate default settings (GL Accounts, Bank Accounts, Addresses, etc.)
Create Financial System User Company(s) | [5 empty] | New User can access financials company(s)
Import GL Accounts (Chart of Accounts) via SF Data Loader
Manually Create and modify existing GL Accounts
Create appropriate Fiscal Year(s) and Periods for each Financial Company
Create Financial Divison Master(s)
Create Financial Project Master(s); confirm auto creation (sync) when new Manufacturing Project is added
Create appropriate Bank Account(s) for each Financial Company
Create appropriate Credit Card Account(s) for each Financial Company
Create Reasons Codes (if applicable)
Create Journal Entry Standard ID (if applicable) | [5 empty] | and create recurring JE templates - ID is associated with JE templates
Create or modify AR Control setting defaults (Accounts, Statements, Finance Charges, Write-off and other settings)
Create or modify AP Control setting defaults (Accounts and other settings)
Create Vendor Class Company for each Vendor Class Master in Manufacturing setting defaults | [5 empty] | create customer class?
Return to Financial Company Master to ensure that proper Vendor Companies and Customer Companies have been auto created when creating new Vendor and Customer Masters in Manufacturing
Review AR Control for appropriate defaults of setting and GL Accounts (Change AR Account Type as needed on GL Accounts)
Review AP Control for appropriate defaults of setting and GL Accounts (Change AP Account Type as needed on GL Accounts)
Add Budgets (if applicable)
Establish Foreign Exchange Schedule (if applicable) for each Financial Company
GENERAL
Create a new Customer and a new Vendor
Run All Tabs, use Customize My Fields button to customize which and what order of tabs at the top of your screen.
Click “Help for this Page” at top right corner of RSF pages to open Online Help.
Access 'Rootstock Resource Center' for additional help and documents.
Ensure that appropriate Dimensions are set on the RSM Company Master (Source and Values) and that the appropriate default values are then set on the source Master objects (e.g. Customer Master, Product Master, Organization Departments, etc.).
ACCOUNTS PAYABLE
For Vendor Invoice sourced from a RS Purchase Order, perform PO-AP Match functions (containing no Variances, along with PO/Invoice Price and PO Receipt/Invoice Quantity Variances), submit to Batch, then Close Batch; then proceed to the auto created RSF Payable Transaction to ensure that Payable Invoices have correctly been processed.
Create a manual, expensed Payable Transaction.
Create a Payable Credit Memo and a Debit Memo manually.
Post all Payable Transactions created above either by Transaction and/or by Session.
Run the AP Aging Report as Forward and/or Backward looking for both 'As of Now' and 'As of a Certain Date'
Change Payment Method on a specific Payable Transaction.
Create a Payment Selection to pay vendor(s) by check.
Print a check.
Create a Payment Selection to pay vendor(s) by electronically and process.
Perform an Open Item Application (of a Vendor Credit Memo).
Review GL Transactions to confirm the transactions were posted correctly.
Demonstrate that you can run the following Payable-related reports and lists (if applicable): Check Register for Single Payment Session, All Payment Types and by Period; Payable Application Transaction Query; Vendor Credit Application Query/Report, Cash Requirements Report, 1099 List.
Generate and Print 1099's.
ACCOUNTS RECEIVABLE
Create and process a Sales Order Prepayment.
Perform a Sales Order Fulfilment (Pick, Pack, Ship and Invoice) on a Sales Order applying SO Prepayment.
Approved, Print and Transfer Sales Order Invoice to AR and validate accurate accounting and Dimensions.
Create and process a Sales Credit Memo sourced from a Sales Order Invoice for credit on an RMA's Product.
Create and process a Sales Credit Memo sourced from a Sales Order Invoice in order to correct the pricing on the Sales Order, then re-fulfill.
Create a Sales Credit Memo manually in RS Financials.
Create a Sales Debit Memo manually in RS Financials.
Post all Receivable Transactions created above either by Transaction and/or using the 'Sales Invoice Review and Mass Post' function.
Run the AR Aging Report as Forward and/or Backward looking for both 'As of Now' and 'As of a Certain Date'
Create a Cash Receipt and Apply to open Invoice using both the 'Cash Receipts' object for multiple customers or 'Quick Cash Receipt' for single customer receipt.
Process Customer Statements and Finance Charges (if applicable)
Demonstrate that you can run the following Receivable-related reports and lists (if applicable): AR Debit/Credit Memo Register, Cash Receipts Journal
GENERAL LEDGER
From the RS Site Map under the Inventory Management section, locate the Inventory Cost Transactions object to view all 'Cost Transactions Types' in order to validate the proper accounting recorded by the RSF GL Transaction.
Create Journals from the Expenses tab to record CC expenses.
Create Journal Entry (JE) Templates (s) for using during the Monthly Period Close Process (if applicable).
Convert JE Templates to JE's for a Period (if applicable) | [5 empty] | This has to be done after the template is created!!!!!!
Create Journals from the Expenses tab to record CC expenses.
Create a manual Journal Entry and Lines for various purposes (e.g. Reversing, etc.)
Cancel/reverse and clone a Journal.
Familiarize yourself with the Bank Reconcilation functionality attempting to Reconcile a few Items and Add a (new) Transaction that can be reconciled.
Demonstrate that you can run the following General Ledger-related reports and lists (if applicable): GL Transaction Inquiry, GL Transaction List View, Postings Summary Report.
MONTH END
Demonstrate that you are able to close a Fiscal Period and Year.
Create a new Fiscal Year and Periods.
Translate Data into Parent Company Currency, if multi-currency and multi-company.
Perform Financial Report Data Roll-up, if mutli-company.
FINANCIAL REPORTING
Demonstrate that you are able to create Report Types and Reports using Standard Salesforce Report object.
Define Financial Report Template(s) using Guide 'Entitled Define Financial Statement Templates v 0.1)
Test Report Templates for Completeness
Run 'Prepare Financial Reports' object on prepared Financial Report Templates.
Display, Print, Export and Purge Finanical Reports
If applicable, demonstrate that you are able to use the "External Data for Financial Reports" object to import and use data that originates beyond RS Financials. | [5 empty] | Financial reports can import and use data that originates beyond the GL, budgets and financial forecasts, and Statement Entries. This data is kept in the External Data Store, where it is assigned an identifying label and a relevant timeframe.
If applicable, demonstrate that you are able to add predefined Sub-line Groups using the "Predefined Subline Group Entry/Maintenance" object for use with RS Financial Reports. | [5 empty] | On report templates, “sublines” contain the actual instructions for retrieving the data shown on each line of the report. A line’s sublines may be as simple as an instruction to read data for a single account or range of account numbers, or they may be very complex, specifying a great many separate accounts. An example of a complex set of sublines could be the instructions needed to retrieve the total cost of sales for a single product line, when it’s spread across thirty individual accounts. If that kind of total is to appear on more than one report, it is often best to use this program to define a Predefined Subline Group which can be invoked by any report with a single command. This practice reduces the time required to enter and maintain report templates and, more importantly, eliminates the difficult problem of keeping multiple complex report templates in sync with one another.
Include BOM / Vault scenarios
Include MRP scenarios
Include A Orders, RTV
Include Interco b/ STB and STE (intersystem?)
Include all RSF / non-ops tasks
Include STE transactions - PROD org will need to be upgraded
System Setup
Review Company Master |  |  | Complete
Review Division Master |  |  | Complete
Add new Manufacturing User |  |  | Complete
Review Order Number Assignments |  |  | Complete
Review Site Master |  |  | Complete
Create a new UOM and UOM conversion |  |  | Complete
Create a new Inventory LOCID and LOCNO |  |  | Complete
Create a new subledger account |  |  | Complete
Create a new Inventory Commodity Code |  |  | Complete
Review shop Calendar |  |  | Complete
Create a new Scrap Reason Code |  |  | Complete
Review System defaults |  |  | Complete
Create a new Credit Term |  |  | Complete
MFG Engineering
Create Engineering Items via Vault ( Includes Inventory Items, Purchasing Items, Products and BOM) |  |  |  | Jim H
Verify Engineering Items and BOM Loaded Correctly |  |  |  | Jim H
Review Engineering Item master for MFG item created |  |  |  | Jim H
Navigate to Inventory item
Navigate to Product Master
Change revision
Review the BOM tree
Query and edit the BOM Master (Phase in / Phase Out) |  |  |  | Jim H
Shop Floor
Create a Routing Master via automation |  |  |  | Jim H
Verify Routing Load Properly |  |  |  | Jim H
Create / Edit a MFG Work Center |  |  | Complete
Create / Edit a MFG Process |  |  | Complete
Create / Edit a MFG Machine Master |  |  | Complete
Create / edit a MFG Labor Grade |  |  | Complete
Create a Routing Operations and assign to a Routing Master |  |  | Complete
Create a standard Routing Operation
Create a Subcontract Routing Operation
Create a Labor Only Routing Operation
Review / Create a MFG Department |  |  | Complete
Create / Edit an Independent Operation |  |  | Complete
Projects
Create Project Status Value |  |  |  | Sam L
Create a Project Master |  |  | Complete
Enter a budget for the Project Master |  |  | Complete
Review Project after posting PO/SO other transactions against |  |  |  | Sam L
MRP
MRP Launch Schedule | [5 empty] | Set to run nightly and or on demand (manual)
MRP Ouput Analysis - Planned Inv Req's | [5 empty] | Inv Req Key Date Focus: Drives priorities
MRP Ouput Analysis - Planned Work Orders | [5 empty] | WO Key Date Focus: Drives priorities, schedule work orders
MRP Ouput Analysis - Exception Messages | [5 empty] | Supply / Demand Decisions
Capacity Planning
Analyze Capacity |  |  |  | Sam L |  | Short and long range resource planning
Manage Capacity Exceptions / Change Work Center or Date |  |  |  | Sam L |  | "Drag" operations from work center to workcenter and/or from date to date to manage caapacity exceptions
Manage Capacity Exceptions / Change Work Center Capacity |  |  |  | Sam L |  | Expand the available capacity within a work center for a specifi period of time to mange the exception (Ex: 12 hour shifts instead of 8 hour shifts over a specifi time frame)
Verify Scheduling Spreadsheet is Updating Properly |  |  |  | Sam L
Inventory Transactions | [5 empty] | Al create inventory transactions. Policy is when do I use one or the other
Location Add |  |  |  | Larry H |  | If average cost, how is the initial average cost being established in thee first time the item hits inventory is through a loction add (no history)?
Location Adjust |  |  |  | Larry H |  | Specific or Variable Adjustment Accounts
Physical Inventory & Reconciliation |  |  |  | Larry H
Cycle Count |  |  |  | Larry H
Backdating |  |  |  | Larry H |  | Process in place to back date transaction
Inventory Management
Review Inventory item masters, fields and tabs |  |  | Complete
Override a Commodity Code value, save, and revert |  |  | Complete
<Acctg> Review Inventory Item accounts |  |  |  | Katie M
Pick an item and find the cost (see Inventory Costing below)
Review the various "Inventory by...." records and note the different information contained in each object
If items are serialized, review the Device History record
Requisitions and Purchasing
Review PO Control Record |  |  | Complete
Review POAP Control |  |  | Complete
Review Vendor Classes, if used |  |  | Complete
Review PO Commodity Codes |  |  | Complete
Create Vendor Master |  |  | Complete
Add multiple addresses and contacts
Add credit terms to customer master
Set up key indicators, accounting info, shipping details, lead times
Add Item Vendor records for vendor; include vendor part number, if known |  |  |  | Ron M
Requisitions |  |  |  | Team
Inventory Requisition Workbench for MRP-generated reqs - query reqs in planned status
Query different ways: by project, by primary or assigned vendor, by due date, etc.
Firm requestion, approve, assign vendor, convert to PO
Create an indirect Purchase Item Master
POs |  |  |  | Lisa & Dee
Find a PO which generated from the requisition
Review Header and line details, including receipt locations by line, addresses in advanced section, etc.
Submit PO for approval - test approval process
Submit PO to vendor
Make a revision to a PO Line qty / cost
resubmit for approval
resubmit to vendor
Create an adhoc PO (not from Reqs) and submit to approval / vendor
Receipts |  |  |  | Steve
Receive the revised PO from above
Receive the adhoc PO from above
Review Cost transaction for GL codes, costs, dimensions, etc.
Reverse a receipt, verify cost transaction is correct
Follow the Money |  |  |  | Katie M
Work Orders and Time Entry |  |  |  | Leads
Sales Order Setup
Review SO Control record |  |  | Complete
Create Customer Master |  |  | Complete
Add multiple addresses and contacts
Add credit terms to customer master
Set sales region, price book, sales person, etc. as req'd on customer master record (might need to set up the Region/person/etc. records before this step)
Review Customer Class records
Review Product Group records |  |  | Complete
Add a miscellaneous / service product |  |  |  | Team
Add Stock Product (either use existing inventory item or create new) |  |  | Complete
Set Pricing
Price on Product Master
Price on Price Book
Other - Customer / Product specific pricing scenarios
Set up shipping options (Carriers, FOB Codes, Freight Terms, etc.) |  |  | Complete
Set up Tax Locations and assign to Customer Master ship to addresses |  |  | Complete
Sales Order Processes
Create SO w/ Stock and Misc/Service line items |  |  |  | Nick
Review pricing
Review additional tab on line
Firm Lines (aka Create Demand)
Add header level external comment
Add Line level external comment
Print Sales Order, review template, email to yourself
Pick, pack line items
Generate SO Picklist Header
Fulfill line items
Create Sales Order Prepayment against the SO |  |  |  | Nick
Print a packing slip |  |  |  | Nick
Create the SO Invoice |  |  |  | Nick
Review the account distribution (GL Accounts)
Review the dimensions line by line
Modify the GL Distribution on a line
Print and review the template (price, tax, discounts, addresses, comments, etc)
Apply SO Prepayment to Invoice
Transfer Invoice to acctg package and review in accounting
Sales & Set Up
Create a sales Order | [5 empty] | Multiple Types?
Validate Price and cost roll ups
Validate material requirement
Validate labor requirements
Manage changes to related work order
Sales Order Cancellation | [5 empty] | More involved than regular sales order as thework order must be dealt with
Inventory Costing
Weighted Avg
Weighted Avg - Project
Weighted Avg - FIFO
CutOver
Load WIP WO |  |  |  | Ron M
Load Open PO's |  |  |  | Ron M
Load Open Customer Orders |  |  |  | Ron M
Load Warehouse Inventory by Location |  |  |  | Ron M
Load Purchase Agreements |  |  |  | Ron M
Load Item/Vendor |  |  |  | Ron M